## Group H (471 Winter 2020)
Activity | Task | Subtask | Subtask description | Status | Estimation | Release | Personas
Simulate 911 call | Lock screen | Create apple UI for lock-screen and emergency calling |  | Todo |  | Release 1 | Child
Simulate 911 call | Lock screen | pressing emergency to get to dial screen |  | Todo |  | Release 1 | Child
Simulate 911 call | Lock screen | Add dog bark to signify the start of 911 call |  | Todo |  | Release 3 | Child
Simulate 911 call | Lock screen | Lock Screen must unlock by entering the 911 pass code |  | Todo |  | Unscheduled Releases | Child
Simulate 911 call | Lock screen | Switch layout to cartoonish drawings |  | Todo |  | Unscheduled Releases | Child
Simulate 911 call | Lock screen | Support multiple language |  | Todo |  | Unscheduled Releases | Child
Simulate 911 call | Dial Number | Auditory/visual reward signifiers | Will take form in bell chirps and green check marks | Todo |  | Release 1 | Child
Simulate 911 call | Dial Number | Only press 9-1-1 in correct sequence |  | Todo |  | Release 1 | Child
Simulate 911 call | Dial Number | Visual queue when wrong number is dialed repeatedly |  | Todo |  | Release 1 | Child
Simulate 911 call | Dial Number | Add "wrong" audio incorrect signifier |  | Todo |  | Release 1 | Child
Simulate 911 call | Dial Number | Screen highlight on correct button to be pressed |  | Todo |  | Release 1 | Child
Simulate 911 call | Dial Number | Support for multiple languages. |  | Todo |  | Unscheduled Releases | Child
Simulate 911 call | Tell operator what emergency it is | Display hints when a button is pressed. | This will be toggleable and hints will be off by default. | Todo |  | Release 1 | Child
Simulate 911 call | Tell operator what emergency it is | Dog box to guide child | By default we would have this on to guide the children through the 9-1-1 call | Todo |  | Release 1 | Child
Simulate 911 call | Tell operator what emergency it is | Auditory/visual reward signifiers |  | Todo |  | Release 1 | Child
Simulate 911 call | Tell operator what emergency it is | Script button to show a default script |  | Todo |  | Release 3 | Child
Simulate 911 call | Repeat personal information to Call operator | Visual hints of house and street | This will be carried on by the use of a dog talking graphic | Todo |  | Release 1 | Child
Simulate 911 call | Repeat personal information to Call operator | Auditory/visual reward signifiers |  | Todo |  | Release 1 | Child
Simulate 911 call | Repeat personal information to Call operator | Shortcut to view parts of address without exiting the call |  | Todo |  | Unscheduled Releases | Child
Application Setup and simulate 911 call | Connect to dummy phone | WiFi Linkage |  | Todo |  | Unscheduled Releases | Firefighter
Application Setup and simulate 911 call | Respond to child | Wizard of Oz implementation |  | Todo |  | Release 3 | Firefighter
Application Setup and simulate 911 call | Respond to child | Display prompts and dialogue | For both firefighter and children. | Todo |  | Unscheduled Releases | Firefighter
Application Setup and simulate 911 call | Respond to child | Display responder script |  | Todo |  | Unscheduled Releases | Firefighter
Application Setup and simulate 911 call | Respond to child | Add another way to view the script |  | Todo |  | Unscheduled Releases | Firefighter
Application Setup and simulate 911 call | Respond to child | Customize dialouge |  | Todo |  | Unscheduled Releases | Firefighter
Take Short Quiz | Pass a short quiz with adequate results (80%) | Include finding address from pictures | Will include houses and appartment. | Todo |  | Release 2 | Child
Take Short Quiz | Pass a short quiz with adequate results (80%) | 3-5 quizes | Multiple choice | Todo |  | Release 2 | Child
Take Short Quiz | Pass a short quiz with adequate results (80%) | What to expect in a 9-1-1 call |  | Todo |  | Release 2 | Child
Take Short Quiz | Recall information to parental supervisors at home | Displaying a graphic of parts of an address |  | Todo |  | Release 3 | Child
Take Short Quiz | Recall information to parental supervisors at home | Add narration on finding address pages |  | Todo |  | Unscheduled Releases | Child
Take Short Quiz | Recall information to parental supervisors at home | Add apartment component |  | Todo |  | Unscheduled Releases | Child
Simulation at home | Simulate 9-1-1 call with the same activities | Wizard of Oz implementation |  | Todo |  | Release 3 | Child Parents
Simulation at home | Simulate 9-1-1 call with the same activities | Release app on app store |  | Todo |  | Unscheduled Releases | Child Parents
Learning extra info | Extra fire safety info | Fun safety tip to display on top of the main menu |  | Todo |  | Release 3 | Child Parents
Learning extra info | Extra fire safety info | Fire alarm safety |  | Todo |  | Unscheduled Releases | Child Parents
Learning extra info | Extra fire safety info | How to safely handle lighters, matches, and other fire starting equipments |  | Todo |  | Unscheduled Releases | Child Parents
Learning extra info | Emergency Exit Exercises | Identify fire exits from pictures |  | Todo |  | Unscheduled Releases | Child Parents
Learning extra info | Emergency Exit Exercises | Choosing |  | Todo |  | Unscheduled Releases | Child Parents
Note on A2: Highest priority
Note on A21: Priority is the 911 simulation calling. Implementaion of phone connectivity will be reserved in a future release.
Note on A35: This will be the lowest priority.

## Releases
Name | Goal | Start date | Release date | Is released | Is archived
Release 1 |  |  |  | True | False
Release 2 |  |  |  | False | False
Release 3 |  |  |  | False | False
Unscheduled Releases |  |  |  | False | False

## Personas
Persona | Group | Details | Picture
Child | elementary school | They are learning how to practice fire safety in the houshold | 4
Candace | Regina Fire Department |  | 0
Parents | Parents |  | 6
Firefighter | Regina Fire Department |  | 23